# Lindale CE Primary School

## School Improvement Plan 2017-2018

Progress reviewed half-termly

Last updated: 6th March 2018

Key

|  | Not yet started / not a current focus |
| --- | --- |
|  | In progress |
|  | Majority accomplished |

| PRIORITY 1 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Continue to develop an exciting, challenging and relevant curriculum |  |  |  |  |  | Outstanding teaching and exciting cross-curricular work with a focus on mastery and application of key skills Greater application and understanding among all staff of a learning culture in which pupils have self-belief and know how to learn High teacher expectations and a belief that all pupils can succeed | - Extend roles of subject leaders and allocate development time - Continue to develop mastery in Maths, learning from NW Maths Mastery Hub - Enrich arts curriculum and submit arts mark application - Develop cross-curricular application of computing skills - Use increased funding to develop outstanding PE provision and impact - Develop planning in new class structure, using Chris Quigley Essentials for key skills planning and assessment in foundation subjects | SC FM KC LO / all AM KL / all | Throughout year | - One day per subject, allocated on rolling programme to ensure adequate development and monitoring of foundation subjects - Staff meeting time - Increased PE funding to allow further development of field | - Book scrutiny - Subject leader blogs and class pages on website and Facebook page show exciting and challenging learning - Termly assessments to measure progress - Governor monitoring including pupil conversations - Arts Mark achieved Monitoring Governors: Curriculum & Standards committee |
| Progress |  |  |  |  |  | December 2017 - Development of Maths Mastery, including joint moderation of Maths books with a Mastery focus and FM involvement in SLRP Mastery group - Registered for Arts Mark. Aim to have evidence for Gold standard by Summer - Status of Lead School for computing re-validated. LO has met with staff to discuss cross-curricular planning, and has taught Internet safety and programming weekly (30 mins) before practical computing lessons - Cross-curricular computing also developed with QR codes in KS2 - PE audit and yearly plan competed March 2018 - Peer monitoring and work scrutiny now more firmly established- 2 Maths and one English now undertaken. Positive impact on all staff supporting each other and sharing best practice as well as peer accountability - Half-yearly reports sent out and used to inform parent converstaions |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 2 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| Increase proportion of pupils meeting ARE and higher standards in all subjects |  |  |  |  |  | Minimum of 75% of pupils meeting ARE in Maths, Reading, Writing and SPAG Minimum of 25% of pupils achieving higher standards, particularly in Reading and Writing Rapid identification of children falling behind, and interventions put in place Use of A3 books for afternoon follow-up for key learning | - Share expectations with staff as part of appraisals - Termly pupil progress meetings - Further use of high-impact training, including Read Write Inc Phonics - Termly monitoring of the impact of interventions - Ensure time is made available to put Reading and Maths intervention training in place - Use teaching students to support interventions in first term | SC Subject leaders All SC All | Termly data tracking, pupil progress meetings and intervention monitoring; half-termly tracking of spelling and writing | - CPD for Read Write Inc - County moderation by KC and FM - Release time to train students in effective Maths and Reading interventions | - Termly data reviews - Pupil progress meetings - Lesson observations - SATs results Monitoring Governors: Curriculum & Standards committee |
| Progress |  |  |  |  |  | December 2017 - Training completed in Read Write Inc, showing impact in Phonics progress - Trainee teachers used to support Reading - Regular additional reading programme for children below ARE - FM and KC applied to be County moderators again March 2018 - FM and KC passed assessment to be County moderators. - KC supporting Selside alongside SC. LA funding to pay for her time. - School invited to be part of ‘Good to great’ project’. We will be working with Penny Bridge Academy. - One to one phonics (RWI) in place for 3 year 2 children and one Year 1 child. SC training Rose Campbell to deliver. |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 3 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| Continue to improve standards in Phonics and Spelling in all year groups |  |  |  |  |  | Minimum of 75% of pupils meeting ARE Children confident in use of Phonic skills and are able to read and write independently All children have a very good grasp of spelling high frequency words, with difficulties no longer slowing their writing Children meeting year group expectations in spelling common exception words and spelling patterns | - Re-introduce daily Phonics and Spelling session in mixed-age groups, and additional Friday session for youngest children - Be very deliberate about catching up any children who have gaps and are falling behind. Daily use of TAs to go over sounds cards and practice blending - Use incidental time such as lining-up to practice flashcards or spelling patterns, making Phonics and Spelling more visible across the school - Ensure that any child who is not reading at home is heard read in school, in addition to reading that other children get - Renew focus on spelling in marking and ensure any continued mistakes are discussed with children - Half-termly monitoring of Phonics and Spelling | All All All All KC KC | Steps taken from September. Termly joint monitoring of all writing at staff meetings | RWI 2 day course £210 Additional flash cards Phonics aprons SPAG.com extended to all year groups £67 | - Half-termly Read Write Inc phonics assessment - Ros Wilson levelled writing shows improvement in spelling criteria - Book scrutiny from staff, subject leader and subject governor Monitoring Governor: Tom Holman |
| Progress |  |  |  |  |  | December 2017 - Interventions and daily Phonics in place for all children up to Y4 who have not mastered them - Daily guided reading in KS1 - Spelling focus evidenced through English book monitoring - March 2017 - Strong on-going spelling focus throughout-out school - Phonics monitoring shows need for greater development of independent spelling strategies (Fred fingers) in EY, and KS1. - KS2 focus on ensuring that commonly mis-spelt words are always picked up for correcting. - ‘Good to great’ project focus with Penny Bridge will be spelling. |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 4 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| Improve children’s knowledge of times tables and instant recall of number facts |  |  |  |  |  | Minimum of 75% of pupils meeting ARE for times tables and number fact knowledge Regular tests show impact of teaching and practice | - All staff including support staff are aware of year group expectations - Regular mental maths sessions and use of homework to reinforce - Use computers and apps to make learning fun - Use support staff to check knowledge - Introduce Big Maths Click challenges and Learn-its - As with Spelling, use incidental times to reinforce learning and ensure that children who are not learning at home receive extra follow-up - Particular focus on current Y3 who will have statutory online tests in summer 2019, and Y2 in readiness | FM All All All All All KC | From September | Continue with Mathletics subscription: £221.76 Big Maths Beat that- resources free. TA time to collate. | - Half-termly times table tests - ‘Big Maths Beat that’ showing improved scores throughout year Monitoring Governor: Helen Churchill |
| Progress |  |  |  |  |  | December 2017 - EY / KS1 regularly using lining-up times to practice number facts - KS2 Big Maths in place – enjoyed by pupils and improving times table knowledge - March 2017 - On-going. Regular practice of number facts and times-tables throughout school. |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 5 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| Continue to develop outstanding behaviour for learning and a growth mindset, underpinned by our school values |  |  |  |  |  | All children are happy, confident, feel successful as learners and are making good choices Children work well independently and as a team and support each other. The atmosphere in school is extremely harmonious | - Build on previous work with school council and Pupil Parliament - Staff make more time to listen to individuals - Further develop role of Y6 as school leaders, including the introduction of John Muir Award - Further develop the roles of classroom helpers, librarians and computer monitors - Encourage children to take greater responsibility in caring for the school and outdoor environment, looking after equipment and tidying up from an early age - Staff provide model care for the school via high standards of displays, well-organised classrooms and equipment sorted - Continue to respond to children’s ideas for clubs, residentials and trips, and involve them in planning | SC All SC All All All All | From September. Leadership training in September and through year | - Pupil Parliament – 4 days at the Parliament venue and staff time: £210 - Y6 leadership training and John Muir Award - Day training with FSC in September £200 - Replace broken / worn-out wet playtime games - Gardening budget £200 | - In pupil conversations, pupils are able to articulate a growth mindset - Work scrutiny shows mastery activities and that children are developing perseverance - Behaviour records continue to show that poor behaviour is extremely rare - Frequent Governor monitoring of learning environment Monitoring Governors: Pastoral & Community Committee |
| Progress |  |  |  |  |  | December 2017 - Continued involvement in Pupil Parliament, including confident participation in debate with John Bercow - Y6 day to develop leadership skills at Castle Head FSC in September - Weekly self-review in KS2, with focus on learning behaviours and values as well as ‘what’ has been learnt - Classroom helper roles established in KS2, along with librarians and digital leaders - John Muir Award work planned with Castle Head FSC - All classes have increased pupils’ involvement in caring for equipment and environment March 2017 - Learning walk with SLRP exec. Officer and LA adviser evidenced outstanding behaviour across school including extremely high levels of engagement. - No behaviour incidents recorded at all except for those relating to some social –communication difficulties leading to misunderstandings. |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 6 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| Develop an Outstanding Early Years environment |  |  |  |  |  | Children make outstanding progress in Early Years Outstanding progress is continued in the transition to Y1 and Y2 through challenge in play and analysis of gaps in early learning skills | - Ongoing training through reading, blog posts and courses on Early Years excellence as available - Regular reflective conversations to help staff understand best practice, with all staff contributing to observations and discussions - Ensure that children with SEN are fully included - Establish new ways of working with new mixed -age class, ensuring enjoyment and high expectations of challenge and achievement - Further develop classroom environment inside and outdoors to meet needs of mixed-age class | FM / KL All FM / KL FM / KL SC / FM / KL | From September, continuing work started in previous year | - Regular staff meeting time with Early Years staff - Planning time for all staff together - Equipment and inside and outdoors resources for mixed-age class - Staff training – ABC Does outdoor learning £185 | - External moderation to ensure learning environment reflects current best practice - Frequent Governor monitoring Monitoring Governor: Lisa Jefferson |
| Progress |  |  |  |  |  | December 2017 - Detailed assessments and gap analysis in place - Fortnightly meetings with all staff to develop team understanding of ‘In the moment planning’ and objective-led learning - Classroom environment changing in line with assessments and gap analysis - Additional resources purchased and introduced, both inside and outdoors - March 2017 - LA moderation support visit. Very impressed with provision, range of activities both focussed and continuous, and engagement of pupils. |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 7 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| Develop outdoor learning environment |  |  |  |  |  | Outdoor environment contributes significantly to learning and behaviour and complements classroom learning More challenging play space and room to run increases children’s fitness Happy playtimes and children engaging in a wide variety of activities | - Develop path around field so that children can run all round - Develop area around oak tree as a reflective space – as part of outdoor learning and in response to pupils’ request for a quiet place - Develop Early Years garden in line with outstanding Early Years provision - Develop garden area for after-school club and KS1 outdoor afternoon. Apply for RHS Schools Award - Develop work on recommendations of Cumbria in Bloom judges | WW KL KL / FM SL SC | Throughout year | - Further Awards for all funding to develop activity trail and develop play area - Fundraisers course for office manager (Paid for by FOLS) - Increased PE funding - Gardening budget £200 | - Cumbria in Bloom entry - RHS Schools Awards - Children’s play and fitness enhanced by greater space Monitoring Governor: Paul Bond |
| Progress |  |  |  |  |  | December 2017 - Some of additional Sports Premium funding used to extend path around remainder of field, enabling children to complete laps in all weather conditions - Wendy Wood started Awards for All application for early Years outdoor equipment and climbing/activity equipment along extended path. Also bid for all-year round grass in FS outdoor area. March 2017 - Path extended to go right around field providing greater opportunities for exercise. - Cumbria in Bloom applied for |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 8 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| Continue to develop as an Outstanding Church School |  |  |  |  |  | Children are more involved in planning and delivering aspects of Collective Worship | - Pupils further develop leadership of Collective Worship in classes and whole school - RE leader works with groups of pupils to plan Collective Worship | SC / KL | Throughout year | - Staff development time | - Children move from planning class worship to whole school worship Monitoring Governor: Jenny Leahy |
| Progress |  |  |  |  |  | December 2017 - Subject leader and governor have met to discuss developing area around the oak tree as a reflective area. - Time in CW planning to allow children to plan their own class worship. March 2018 - Moving mountains – Cumbria Mission in for CW - HT part of church heads/clergy breakfast half-termly – various speakers on church school issues |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 9 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| Further develop outward-looking mindset for the benefit of pupils and staff |  |  |  |  |  | Pupils feel connected with others in local schools Staff develop best practice and share expertise and support others Staff leadership skills developed | - More work with cluster schools for moderation and shared projects - Continued involvement in SLRP and LASL, including peer reviews and support - Involvement in Schools Direct teacher training and University of Cumbria - SC to train teachers in Reading Intervention - More participation in South Lakes Pupil Parliament - Staff to be County moderators - LLE role supporting other schools to develop subject to demand and capacity - Computing teacher to develop and deliver further training courses for teachers. | All SC FM / KC SC All All SC | Throughout year | - Staffing to enable small groups of children to take part in events such as pupil parliament or Year 6 leadership day. | - School takes a lead role in sharing expertise with other colleagues - This in turn sharpens practice in-house Monitoring Governor: Helen Churchill |
| Progress |  |  |  |  |  | December 2017 - SC working with Selside School two days each week in LLE role - County moderator applications submitted - Reading Intervention course underway - Peer review completed and peer support for HT Performance Management with St Mary’s in Kirkby Lonsdale - March 2018 - SC continuing as EHT of Selside School until July 2018 - KC supporting Selside as SLE – LA funded - Lindale staff supporting other Selside staff through visits to school- all key stages and office manager. - SC continuing on PHA executive - Reading intervention course completed. |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 10 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| Maintain expertise in governance and further develop monitoring role |  |  |  |  |  | Governors are confident in their roles of support and challenge | - Governor training and networking via active participation in Cluster, SLRP and CASL - Induction training for all new Governors - Annual audit of Governor skills to inform roles, and recruit to gaps - Regular monitoring, linked to subject areas and School Improvement Plan | Govs / Clerk Govs / Clerk Govs / Clerk Govs | Throughout year | Cartmel Cluster governance group – courses approx. £20 per head Courses through the LASL and SLRP. Diocesan and LA training as relevant | - Governors are increasingly knowledgeable and effective in monitoring and support - New governors appointed to fill any gaps in expertise Monitoring Governor: Helen Churchill |
| Progress |  |  |  |  |  | December 2017 - Governor skills audit completed and weaker areas identified for new Governor recruitment March 2018 - Regular monitoring, learning walks, and work of committees ongoing. |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 11 |  |  |  |  |  | Desired impacts | Key steps | Staff | Timeframe | Resources | Measures of success |
| Be financially sustainable whilst maintaining high quality of provision |  |  |  |  |  | School is held in very high local regard More people in the community are aware that there is a school in Lindale Children are attracted to the school from outside the village | - Raise profile of the school via regular posts on website and Facebook, regular contributions to Grange Now and publicity through local media - Half-termly ‘Toddler Taster’ sessions - Open days in Autumn term - Further strengthen links with Pre-School - Maintain specialist staff | All / Govs All All SC / KL / FM SC | Throughout year | - Minimal budget for advertising and promoting events | - Evidence of engagement with website and Facebook - Improved pupil numbers Monitoring Governors: Finance & Staffing Committee |
| Progress |  |  |  |  |  | December 2017 - Regular updates to school website and Facebook throughout Autumn term - Paid Facebook posts to advertise Early Years provision - Nursery numbers increasing - Monthly contributions to Grange Now - Lead School for computing status promoted via Grange Now and Facebook posts - New Facebook page for Friends of Lindale School March 2018 - Regular updates to school website and Facebook throughout Spring term - Monthly contributions to Grange Now |  |  |  |  |  |
| Autumn Spring Summer |  |  |  |  |  |  |  |  |  |  |  |